## Slide 1: Investigating Sales Lag and Formulating Growth Strategies for Product C8500
Task | Owners | Deliverables | Task Length (Weeks)
Define project objectives and scope | Project Manager | Project Charter | 0.5
Identify key stakeholders and assign team roles | Project Manager | Stakeholder Map & Team Assignment | 0.5
Collect historical sales data for the product | Data Analyst | Cleaned Sales Dataset | 1
Analyze sales trends (YoY and regional breakdown) | Business Analyst | Sales Analysis Report | 1
Conduct internal interviews with sales & marketing teams | Research Lead | Interview Summary | 1
Review customer feedback and product satisfaction data | Research Analyst | Customer Insight Report | 1
Perform competitor product analysis and market trends review | Market Analyst | Competitor Benchmark Report | 1
Identify possible root causes of sales decline | Business Analyst | Root Cause Analysis Summary | 1
Conduct stakeholder workshop to brainstorm potential solutions | Project Manager | Workshop Notes | 0.5
Develop strategic recommendations to increase product sales | Full Project Team | Action Plan Document | 1
Prepare and deliver final presentation to leadership | Project Manager | Final Report & Presentation Slides | 0.5

## Slide 2: Investigation and Recommendation Project – Low Sales Product
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Data Analysis Completed
Final Presentation Delivered
Define project scope & objectives
Identify stakeholders
Assemble project team
Project Initiation
Develop research plan
Design data collection methods
Project Planning
Project Execution
Collect internal sales data
Conduct stakeholder interviews
Analyze market trends
Synthesize findings
Duration (Weeks)
Project Close
Develop and present recommendations
Project Monitoring
Review progress & update stakeholders